## SHO-table-rehabilitation
Table 2: Report Phase II Rehabilitation
| Country | Haiti
Sectors 1 | Locations | Names implementing partner(s) | Output 2 |  |  |  |  | Beneficiaries3
|  |  | Planned | Achieved to date November 2010; Report 3 | Achieved to date December 2011; report 4 | Achieved to date - XXX ; Report 3 | Achieved to date December 2012; report 5 | Planned No. of Beneficiary Households | Achieved to date - November 2010; Report 3 | Achieved to date December 2011; report 4 | Achieved to date December 2012; report 5 | Achieved to date - XXX; Report 3
1. Health | Leogane: Masson, Macombe, Luitor and Croix des Peres | CRWRC | 20 community leaders receive training in psycho-social counselling with an emphasis on post-disaster trauma. SHO funds support the implementation of 9 workshops | a total of 18 people were trained during 3 workshops; 29 psychosocial sessions were held, a total of 1,606 participants ( 645 women, 232 girls, 529 men and 200 boys) | a total of 16 people were trained during 3 workshops; 33 psychosocial sessions were held, a total of 1,686 participants ( 691 women, 239 girls, 550 men and 206 boys) |  | a total of 16 people were trained during 3 workshops; 33 psychosocial sessions were held, a total of 1,686 participants ( 691 women, 239 girls, 550 men and 206 boys) | 20 leaders (4communities) | 1,606 participants | 1,686 people | 1,686 people
2. Water & Sanitation | Gressier, Leogane (Masson, Macombe, Luitor and Croix des Peres), Petit Goave and Grand Goave | CRWRC; VNG-I; PROTOS/ITECA | SHO funds support the construction of 4 permanent latrines and 4 bore holes and pumps | 8 community latrines (4 stalls each) and 4 bore holes and pumps | 8 community latrines (4 stalls each) and 4 bore holes and pumps; 6 com latrines have been destroyed since construction and are no longer in use |  | 8 community latrines (4 stalls each) and 4 bore holes and pumps; 6 com latrines have been destroyed since construction and are no longer in use | 4 communities | 4 communities (14,245 individuals) | 258 households (latrines) and 508 HH (bore holes and pumps) | 258 households (latrines) and 508 HH (bore holes and pumps)
|  |  | 35 missions + capacity support on management of drinking water, rain and storm water and watersheds; and on waste management | NA | 10 missions realised; more than 25 professionals (DATIP and federations) trained (17% SHO funds) |  | 22 missions realized, more than 25 professionals (DATIP and associations) trained (17% SHO funds) | 4 municipalities | NA | 4 municipalities | 4 municipalities
|  |  | water system repaired; water recollection reservoirs built; instruction given on hygienic sanitation and hygiene habits | NA | All water kiosks are working, 200 meters of trenches were dug; 20 rain water cisterns installed; trainings given and information shared via community-based organisations and water committees |  | All water kiosks are working, 1400 meters of water works reconstructed; 40 rain water cisterns installed; trainings given and information shared via community-based organisations and water committees | 4,000 families (27% with SHO funds) | NA | 1,080 HH (water kiosks) and 6 families (rain water reservoirs) | 1,080 HH (water kiosks) and 12 families (rain water reservoirs)
3. Food security & nutrition
4. Livelihood & household security | Jacmel area; Carrefour; Port-au-Prince | VSF-CICDA; GRUEEDH; GARR | 350 vulnerable families located in urban and peri-urban Jacmel receive agricultural inputs and relevant trainings for the production and preparation of vegetables (50% with SHO funds) | 350 beneficiaries selected in Jacmel area; 84 voluntary helpers trained on vegetable gardering; 350 beneficiaries received tools and seeds (50% with SHO funds) | 450 beneficiaries received tools and seeds; 84 voluntary helpers trained on vegetable gardening (50% with SHO funds) |  | 450 beneficiaries received tools and seeds; 84 voluntary helpers trained on vegetable gardening (60% with SHO funds) | 350 households, 1750 people (50% SHO funds) | 350 households, 1750 people (50% with SHO funds) | 225 households, 1,125 people | 225 households, 1,125 people
|  |  | income generating activities are implemented | NA | NA |  | 150 persons received grants to expand their small businesses | 150 families | NA | NA | 150 families
|  |  | non-traditional vocational training for young women | NA | NA |  | 30 women and 10 men have been selected for the vocational training | 40 young women | NA | NA | (training starts in 2013)
5. Education | Leogane, Gressier, Grand Goave; Port-au-Prince; Gressier and Delmas; Port-au-Prince and surrounding areas | FCA; GARR; Zanmi Timoun; Turtletree; PCF | construction of 4 schools (1 with SHO funding); cash for work participation in construction; school building available for hurricane shelter | NA | 1 school completed; parents participated in construction; school building is hurricane and flood shelter |  | 4 schools completed; parents participated in construction; school buildings are hurricane and flood shelter (1 school with SHO funds) | 1,150 students, 100 teachers, 1,680 community members; 5,000 persons provided hurricane shelter | NA | 350 students, 18 teachers; 540 community members (cash for work); 1,248 community members (shelter access) | 1,400 students, 100 teachers (40% female), 640 community members (50% women); 5450 persons provided hurricane shelter (25% with SHO funding)
|  |  | literacy training for adolescents and female merchants | NA | NA |  | 60 persons (59 women and 1 men) have received literacy courses. | 100 adolescents and 100 female merchants | NA | NA | 60 persons
|  |  | 150 young people vocationally trained | NA | NA |  | 180 young people have started their courses | 150 young people | NA | NA | 180 young people
|  |  | 5 workshops on audivisual techniques, 40 participants | NA | NA |  | 3 workshops | 40 young journalists | NA | NA | 24 young journalists
|  |  | library collections and archives restored. 250 people trained | NA | NA |  | July 2010 25 persons trained; April 2012 15 persons trained; 400.000 items received first aid | 250 people | NA | NA | 80 people trained
6. Shelter | Leogane: Masson, Macombe, Luitor and Croix des Peres; Jacmel area: Cap Rouge and Michineau; Gressier, Léogane, Grand-Goave and Petit-Goave; Boen & Ganthier; Gressier: Ti Boucan; Tabarre; Jacmel: Embouchure | CRWRC; VSF-CICDA; LWF; SSID; ITECA; IOM; ESFH; Concertaction | SHO funds support the rehabilitation of 120 houses and the construction of 180 houses | construction of houses is ongoing; rehabiliation of houses will start in January 2011 | with the available funding 121 houses have been repaired; 219 houses have been constructed |  | with the available funding 121 houses have been repaired; 219 houses have been constructed | 300 households, 1 500 people | 90 households | 340 households | 340 households
|  |  | 110 rural houses adapted to local environmental risks are built in cooperation with the targeted families and the communities. | a prototype house built and given to one family; 20 beneficiaries selected; building of 29 houses is continuing; 30 craftsmen trained; 3 teams of builders and carpenters formed | 51 houses completed; 30 craftsmen trained |  | 76 houses completed; 30 craftsmen trained (60% with SHO funds) | 110 households, 550 people | 21 households; 30 craftsmen | 51 households; 30 craftsmen | 76 households; 30 craftsmen (60% with SHO funds)
|  |  | 350 families receive vouchers for house repair; 150 families receive vouchers for house rental; 475 moveable shelters and 800 durable shelters constructed (10% of which with SHO funds) | NA | 400 families received vouchers for house rental; 1297 families received temporary shelter support; 471 families have benefited from materials for and construction of movable semi-permanent shelters (10% with SHO funds) |  | 400 families received vouchers for house rental; 1297 families received temporary shelter support; 471 families have benefited from materials for and construction of movable semi-permanent shelters (10% with SHO funds); furniture for community center in newly built model village | 1775 families (10% of which with SHO funding) | NA | 2168 families (10% of which with SHO funding) | 2168 families (10% of which with SHO funding)
|  |  | 54 houses to be constructed; 54 latrines to be built (9 of each with SHO funds) | NA | NA |  | 16 houses and 10 latrines built (5 houses and 3 latrines with SHO funds) | 54 families (16 with SHO funds) | NA | NA | 16 families (5 with SHO funds)
|  |  | 50 permanent houses, including water tank and ventilated improved pit latrine to be constructed | NA | NA |  | 50 permanent houses built, including water tank and ventiliated pit latrine | 50 households | NA | NA | 50 households
|  |  | 300 families living in camps will move into durable housing | NA | NA |  | 395 families selected; the move of 285 families has been completed | 300 households | NA | NA | 285 households
|  |  | 48 houses to be constructed | NA | NA |  | construction of 5 houses completed | 48 families | NA | NA | 5 households
|  |  | 25 houses to be built, among which two for the radio station and one for the CASEC | NA | NA |  | NA | 22 families | NA | NA | NA
7.Disaster management | Forêt des Pins, Macaga, 9e and 10e Palm, nd Binot (Petit-Goave), Oranger (Léogane); Port-au-Prince | LWF; Turtletree; Concertaction | provide disaster risk reduction training and assist communities in developing risk reduction measures | NA | 5 communes have received support to enhance their resilience to natural disasters through DRR measures |  | 5 communes have received support to enhance their resilience to natural disasters through DRR measures | 12,800 beneficiaries | NA | 12,556 beneficiaries | 12,556 beneficiaries
|  |  | 1 documentary and 15 short videos on the reconstruction; presentation of videos on 50 locations (schools, camps) | NA | NA |  | 2 documentaries and 11 videos produced; 16 schools visited | NA | NA | NA | 499 students have attended video screenings and discusson on rehabilitation
|  |  | 2 radio stations to be equipped and trained to broadcastdaily information on DRR | NA | NA |  | NA | 40000 | NA | NA | NA |  | 2 radio
8. Protection | Carrefour; Port-au-Prince; Fond des Nègres, Desruisseaux, Vialet, Petit Goave, Carrefour, Petite Place and Lafferonnay | GRUEEDH; POHDH; GARR; TSA | community school offers psycho-social support, recreational activities and information on children's rights | NA | NA |  | 100 children received psycho-social support and were informed on children's rights | 500 children | NA | NA | 100 children
|  |  | inform camp residents of their rights; produce reports on HR situation | NA | meetings held in 30 camps; 3 reports produced; press conferences and meetings with government and MINUSTAH staff held |  | meetings held in 30 camps; 6 reports produced; press conferences and meetings with government and MINUSTAH staff held; 20 programs broadcasted on radio and television; 3.000 leaflets distributed; 3 workshops held | NA | NA | 350 camp residents | 984 camp residents
|  |  | Promote rights of 5,000 IDPs (special attention for children, youth, women and PLWHAs | NA | NA |  | 457 children trained on human rights, sexual education, hygiene, cholera prevention; 250 women informed about women's rights and domestic violence; 50 advisors (40 women and 10 men) trained on violence against women, HIV/AIDS and reproductive rights | 5,000 beneficiaries | NA | NA | 457 children, 250 women, 50 advisors
|  |  | Appropriate management structure and staff are in place; 2,400 (25 months x 8 locations x 3 times a week) activities implemented per age group; 4 x a year mass group events; 2 parents meetings in each community | NA | Staff and structure in place; Between January and September 2011 433 meetings took place at 7 locations, and attended by 38.228 children; 5 mass events organized: carnival + feast of the flag; 12 meetings |  | Staff and structure in place; between January 2011 and December 2012 1589 meetings took place at 8 locations, and attended by 136.065 children; 58 mass group events: carnival, Christmas, sports, museums; | 1,000 children and adolescents (77% with SHO funds) | NA | 674 children, 423 parents | 1628 children, 991 parents (77% with SHO funds)
|  |  | 12 program trainings for staff; Community leaders encouraged to participate; Knowledge and experience exchanged with other NGOs | NA | 2 seminars and 2 workshops took place; Meetings with community leaders; 3 NGOs were contacted |  | 2 seminars and 2 workshops took place; Meetings with community leaders; 3 NGOs were contacted. 6 additional trainings took place, each training was given several times (at different locations) | 70 fieldworkers (77% with SHO funds) | NA | 54 fieldworkers | 66 fieldworkers (77% with SHO funds)
9. Program management & support (at field level) | Les Palmes:Gressier, Léogane, Petit-Goave, Grand-Goave; Pétion-Ville | VNG-I: ACT Alliance; ICCO & Kerk in Actie; NCA | 4 termporary municipal offices and 1 DATIP office + running costs | NA | offices under construction |  | municipal offices are still under construction; DATIP office is installed and running | NA | NA | NA | NA
|  |  | Support to local government associations | NA | preliminary meetings have been held |  | the newly hired municipal technicians receive extensive training | NA | NA | NA | NA
|  |  | members of international alliance coordinate interventions | NA | coordinated interventions took place, + monthly meetings |  | project ended, no longer applicable | NA | NA | NA | NA
|  |  | direct support to partner organisations | NA | partner organisations have been supported |  | partner organisations have been supported | NA | NA | NA | NA
|  |  | recruit additional WG members;support of internal coordination of the WG; assis local implementing organizations (PCM, PME etc.); introduce capacity building, also on DRM, CoC etc; participation in relevant platforms and networks | NA | NA |  | 5 additional members were recruited; 3 meetings were held, + field visits; several WG meetings took place; CoC etc. were dicsussed with prospective participating organizations. | NA | NA | NA | NA
200
125
100

## SHO-table-emergency
Table 1: Report Phase I Emergency
|  | Country |  | Haiti
Sectors 1 | Sub sectors | Locations | Location | Names implementing partner(s) | Output 2 |  |  |  |  | Beneficiaries3
| CDE: not necessary for reporting. Used to organise info |  |  |  | Planned | Achieved to date - XXX ; Report 3 | Achieved to date November 2010; Report 3 | Achieved to date December 2011; Report 4 | Achieve to date December 2012; report 5 | Planned No. of Beneficiary Households | Achieved to date - XXX; Report 3 | Achieved to date - November 2010; Report 3 | Achieved to date - December 2011 Report 4 | Achieved to date - December 2012; Report 5
1. Health | Primary health care | Port au Prince (St Martin area), Petit Goave, Jacmel | Port au Prince, Petit Goave, Jacmel: Saint Martin, Delmas 33, Christ-Roi, Liavois = (Croix des Bouquets), Belladere, Lascahobas, Thomassique & Fond Verrettes; Deschappel (Artibonite valley); Montrouis, Cap Haitien, Les Cayes | TSA; Christian Aid with GARR, NASF | 1,200 people receive medical aid from team of 14 surgeons and several nurses, paramedics and other specialists. |  | 10 qualified staff available for 7 weeks. | 10 qualified staff available for 7 weeks. | 10 qualified staff available for 7 weeks. | 200 surgeries planned daily, mainly amputations (about 12,000 surgeries over a period of 2.5 months) by the team of 14 |  | As a whole, average 225 minor surgeries performed daily, 100 patients seen daily for illnesses, 535 patients received care after coming back to camps from Haiti hospital. (SHO contributed to the care of about 3,000 out of the over 20,000 people who received medical care during the first 2.5 months) | As a whole, average 225 minor surgeries performed daily, 100 patients seen daily for illnesses, 535 patients received care after coming back to camps from Haiti hospital. (SHO contributed to the care of about 3,000 out of the over 20,000 people who received medical care during the first 2.5 months) | As a whole, average 225 minor surgeries performed daily, 100 patients seen daily for illnesses, 535 patients received care after coming back to camps from Haiti hospital. (SHO contributed to the care of about 3,000 out of the over 20,000 people who received medical care during the first 2.5 months)
|  | Port au Prince (St Martin area), Petit Goave, Jacmel |  |  | Various babies to be delivered |  | 18 babies were delivered | 18 babies were delivered | 18 babies were delivered | NA |  | 18 babies | 18 babies | 18 babies
[5 empty] | 2,000 IDPs in the Artibonite valley receive medical aid in Hôpital Albert Schweitzer |  | More than 1,000 IDPs received medical aid, in most cases requiring surgery. | More than 1,000 IDPs received medical aid, in most cases requiring surgery. | More than 1,000 IDPs received medical aid, in most cases requiring surgery. | 2,000 people to receive medical aid, many requiring surgery. |  | More than 1,000 IDPs received medical aid, most of whom required surgery. HAS etablished a prothetics service, which since March 2010 has provided more than 550 new legs for earthquake victims (SHO contributed to the medical care for over 1,000 IDPs) | More than 1,000 IDPs received medical aid, most of whom required surgery. A prothetics service was established, which since March 2010 has provided more than 550 new legs for earthquake victims (SHO contributed to the medical care for over 1,000 IDPs) | More than 1,000 IDPs received medical aid, most of whom required surgery. A prothetics service was established, which since March 2010 has provided more than 550 new legs for earthquake victims (SHO contributed to the medical care for over 1,000 IDPs)
| cholera prevention |  |  | POZ; VKM | 1,500 people living with HIV/Aids informed about prevention of cholera; 4 radio spots about cholera prevention and disaster preparedness and 64 radio programs of 1 hour duration to be broadcasted; training in cholera prevention for community members and health educators |  | NA | 3,848 PLWHAs were informed and when esteemed necessary referred to treatment centre; 4 radio spots broadcasted 7 times a day for 5 months or a total of 840 times; 64 radio programs of 1 hour duration broadcasted; 60 community members and 10 health workers trained in cholera prevention | 3,848 PLWHAs were informed and when esteemed necessary referred to treatment centre; 4 radio spots broadcasted 7 times a day for 5 months or a total of 840 times; 64 radio programs of 1 hour duration broadcasted; 60 community members and 10 health workers trained in cholera prevention and in how to use a megaphone | 1,500 PLWHA;between 70.000 and 120.000 radio listeners; 60 community members + 10 health workers |  | NA | 3,848 PLWHAs informed; 75.000 radio listeners; 60 community members and 10 health workers | 3,848 PLWHAs informed; 100.000 radio listeners; 60 community members and 10 health workers
| Psychosocial assistance | Port au Prince and surroundings areas: Delmas 33, Christ-Roi, Liavois = (Croix des Bouquets), Belladere, Lascahobas, Thomassique & Fond Verrettes |  | Christian Aid with GARR | Psychosocial support to those within target population that request it (500 people) |  | 572 people benefitted from psychosocial support (400 children + 172 adults, from which 128 women) | 572 people benefitted from psychosocial support (400 children + 172 adults, from which 128 women) | 572 people benefitted from psychosocial support (400 children + 172 adults, from which 128 women) | 500 people |  | 572 people | 572 people | 572 people
2. Water & Sanitation | Water | Port au Prince and surroundings areas | Port au Prince, Petit Goave, Jacmel: Saint Martin, Delmas 33, Christ-Roi, Liavois = (Croix des Bouquets), Belladere, Lascahobas, Thomassique & Fond Verrettes | TSA; Christian Aid with GARR | Repair of 5 water points |  | 2 water points repaired and 1 newly constructed | 2 water points repaired and 1 newly constructed | 2 water points repaired and 1 newly constructed |  |  | 150 people | 150 people | 150 people
|  | Port au Prince and surroundings areas |  |  | Provision of water purifiers and water for 3 months |  | 1,200 people received water purifying tablets, 600 families received water containers | 1,200 people received water purifying tablets, 600 families received water containers | 1,200 people received water purifying tablets, 600 families received water containers | 1,500 families |  | 1,200 people in Lilavois and border area, and 600 families in Delmas 33, Christ Roi and Lilavois | 1,200 people in Lilavois and border area, and 600 families in Delmas 33, Christ Roi and Lilavois | 1,200 people in Lilavois and border area, and 600 families in Delmas 33, Christ Roi and Lilavois
|  | Port au Prince (St Martin area), Petit Goave, Jacmel |  |  | Four 10,000-gallon water purification systems are now installed and provide daily 200,000 liters of fresh water |  | 4 purification units with a daily capacity of 10,000 gallon each (2 water systems paid with funding of SHO) | 4 purification units with a daily capacity of 10,000 gallon each (2 water systems paid with funding of SHO) | 4 purification units with a daily capacity of 10,000 gallon each (2 water systems paid with funding of SHO) | Not known at planning stage |  | 10,000 out of 23,000 Haitians assisted by the entire programme | 10,000 individuals | 10,000 individuals
| Sanitation | Port au Prince and surroundings areas |  |  | Cleaning of sites (1 to Port-au-Prince and 2 at the border) |  | 3 drainage systems in Christ Roi | 3 drainage systems in Christ Roi | 3 drainage systems in Christ Roi | Not known at planning stage |  | 570 families (3,800 individuals: 2,800 women and 1,000 men) | 570 families (3,800 individuals: 2,800 women and 1,000 men) | 570 families (3,800 individuals: 2,800 women and 1,000 men)
|  | Port au Prince and surroundings areas |  |  | Purchase of waste removal material |  | wheelbarrows, gloves, spades and plastic bags provided to Christ Roi and two border camps | wheelbarrows, gloves, spades and plastic bags provided to Christ Roi and two border camps | wheelbarrows, gloves, spades and plastic bags provided to Christ Roi and two border camps | not known at planning stage |  | 600 famiies | 600 families | 600 families
3. Food security & nutrition | Food aid | Port au Prince and surroundings areas | Port au Prince, Petit Goave, Jacmel: Saint Martin, Delmas 33, Christ-Roi, Liavois = (Croix des Bouquets), Belladere, Lascahobas, Thomassique & Fond Verrettes | TSA; Christian Aid with GARR | Provision of dry food to 7200 people for one month (2,200 with SHO support) |  | 8,720 individuals received dry food ration or a cash voucher to purchase food for one month | 8,720 individuals received dry food ration or a cash voucher to purchase food for one month (2,660 with SHO support) | 8,720 individuals received dry food ration or a cash voucher to purchase food for one month (2,660 with SHO support) | 7,200 people (2,200 with SHO support) |  | 8,720 individuals (SHO contributed to 30,5% = 2,660) | 2,660 individuals | 2,660 individuals
|  | Port au Prince and surroundings areas |  |  | Provision of a hot meal to 400 people for one month |  | 400 children between 3 and 15 received a hot meal from Monday to Friday for 16 weeks | 400 children between 3 and 15 received a hot meal from Monday to Friday for 16 weeks (200 with SHO support) | 400 children between 3 and 15 received a hot meal from Monday to Friday for 16 weeks (200 with SHO support) |  |  | 400 children (100%) | 200 children | 200 children
|  | Port au Prince and surroundings areas |  |  | Not planned originally |  | 2115 individuals including 1228 women, 87 men and 800 children have received a hot meal during Woman Day | 2115 individuals including 1228 women, 87 men and 800 children have received a hot meal during Woman Day | 2115 individuals including 1228 women, 87 men and 800 children have received a hot meal during Woman Day | not planned originally |  | 2115 individuals including 1228 women, 87 men and 800 children have received a hot meal during Woman Day | 2115 individuals including 1228 women, 87 men and 800 children have received a hot meal during Woman Day | 2115 individuals including 1228 women, 87 men and 800 children have received a hot meal during Woman Day
|  | Port au Prince (St Martin area), Petit Goave, Jacmel |  |  | 2.2 Million MRE’s (Meals Ready-to-Eat) have been sent to Haiti for distribution in the compound in Saint Martin and a few satellite distribution centres, reaching 20,000 persons in total. |  | 2.3 million of MRE’s were sent to Haiti for distribution and 2.3 Million were distributed to the target group (1.485.000 meals paid with SHO funds) | 2.3 million of MRE’s were sent to Haiti for distribution and 2.3 Million were distributed to the target group (1.485.000 meals paid with SHO funds) | 2.3 million of MRE’s were sent to Haiti for distribution and 2.3 Million were distributed to the target group (1.485.000 meals paid with SHO funds) | 260,000 meals (approx. 3000 food boxes) is the average of distribution in a given day in Port au Prince, in 4 hours, with support of volunteer staff and the UN. |  | 15,000 people; Enough food was distributed to last for two or three days at a time. Including 18,400 MRE’s daily and 262,102 meals consisting of Rice and Beans with an additional 4,539,084 meals delivered as a Rice Soup mixture to date (1.485.000 meals and 2,240 barrels of corn oil paid with SHO funds) | 15,000 people; Enough food was distributed to last for two or three days at a time. Including 18,400 MRE’s daily and 262,102 meals consisting of Rice and Beans with an additional 4,539,084 meals delivered as a Rice Soup mixture to date (1.485.000 meals and 2,240 barrels of corn oil paid with SHO funds) | 15,000 people; Enough food was distributed to last for two or three days at a time. Including 18,400 MRE’s daily and 262,102 meals consisting of Rice and Beans with an additional 4,539,084 meals delivered as a Rice Soup mixture to date (1.485.000 meals and 2,240 barrels of corn oil paid with SHO funds)
4. Livelihood & household security | Agriculture | Southern Department including, Saint-Louis du Sud: rural village hosting IDPs, Torbeck: the urban town of Torbeck, the rural villages of Ducis, Bereau, Chantal, villages of Fonds Palmiste, Carrefour Canon and Camp Perrin, Rural village of Levy Mersan and Champlois | Port au Prince, Petit Goave, Jacmel: Saint Martin, Delmas 33, Christ-Roi, Liavois = (Croix des Bouquets), Belladere, Lascahobas, Thomassique & Fond Verrettes, Carrefour | TSA; Christian Aid with GARR and KORAL; ADRA | Livestock distribution (200 cows, 600 sheep and goats, 1,500 cockerals, 15,000 chickens) |  | 1,500 cockerals and 15,000 chickens were distributed | 1,500 layers, 15,000 chickens, 220 cows and 640 sheep and goats were distributed (50% SHO funding) | 1,500 layers, 15,000 chickens, 220 cows and 640 sheep and goats were distributed (50% SHO funding) | 1215 families |  | 450 beneficiaries (242 women) | 1,914 beneficiaries (841 IDPs and 1,073 host families); 957 SHO funds | 1,914 beneficiaries (841 IDPs and 1,073 host families); 957 SHO funds
|  | Southern Department |  |  | Distribution of 300 bales fodder; and 1,400 bags of chicken food |  | 1,508 bags of chicken food distributed | 1,508 bags of chicken food distributed, and 540 fodder plots establishedin order to feed cows, sheep and goats (SHO funds 50%) | 1,508 bags of chicken food distributed, and 540 fodder plots establishedin order to feed cows, sheep and goats (SHO funds 50%) |  |  | 450 beneficiairies (242 women) | 1,914 beneficiaries (841 IDPs and 1,073 host families), 957 SHO funds | 1,914 beneficiaries (841 IDPs and 1,073 host families), 957 SHO funds
|  | Southern Department |  |  | Start-up funds for 2 dairies; training in dairy |  | Dairy component no longer feasible, has been removed
|  | Southern Department |  |  | Training for livestock and poultry rearing |  | training sessions held (food, reproduction, animal health etc.) | beneficiaries trained in husbandry techniques: chicken rearing, management of community shop, micro credit, etc. | beneficiaries trained in husbandry techniques: chicken rearing, management of community shop, micro credit, etc. |  |  | 500 people participated in livestock training and 450 people in poultry training | 957 beneficiaries | 957 beneficiaries
|  | Southern Department |  |  | Construction of pens for rearing poultry |  | 30 pens for poultry constructed | 180 pens constructed (90 with SHO funds) | 180 pens constructed (90 with SHO funds) |  |  | 300 beneficiaries (178 women), 50% with SHO funds | 225 people | 225 people
|  | Port au Prince and surroundings areas |  |  | Recapitalisation of small business people for 200 sellers |  | 350 women and 53 men received 10,000 HTG each | 350 women and 53 men received 10,000 HTG each (201 with SHO funds) | 350 women and 53 men received 10,000 HTG each (201 with SHO funds) |  |  | 403 people (201 SHO support) | 201 people | 201 people
|  | Port au Prince and surroundings areas |  |  | Purchase of seeds and agricultural tools for 125 farmers |  | 117 men and 83 women | 117 men and 83 women | 117 men and 83 women |  |  | 200 people | 200 people | 200 people
|  | Port au Prince and surroundings areas |  |  | Purchase of of livestock to 100 rearers |  | 104 women and 153 men received either 1 cow or 2 sheep | 104 women and 153 men received either 1 cow or 2 sheep (50% with SHO funds) | 104 women and 153 men received either 1 cow or 2 sheep (50% with SHO funds) |  |  | 257 people (half with SHO funds) | 129 people | 129 people
|  | Port au Prince and surroundings areas |  |  | Micro enterprise for 50 youth |  | 30 young people received a grant of $ 900 | 30 young people received a grant of $ 900 | 30 young people received a grant of $ 900 |  |  | 30 people | 30 people | 30 people
|  | Port au Prince and surroundings areas |  |  | Training related to economic activities for 500 people |  | 357 individuals trained in ecnomic activities (NB 57 additional individuals received livestock farming training) | 357 individuals trained in ecnomic activities (NB 57 additional individuals received livestock farming training) | 357 individuals trained in ecnomic activities (NB 57 additional individuals received livestock farming training) |  |  | 357 people | 357 people | 357 people
| Other, non food, household items | Port au Prince and surroundings areas |  |  | Provision of food assistance in the form of cash ($52/family) to 2400 adults for 2 months ; 1200 people in Port au Prince, 1200 people in surrounding areas |  | 1,934 families received $60 cash each for a month's food ration | 1,934 families received $60 cash each for a month's food ration | 1,934 families received $60 cash each for a month's food ration | 2400 people (heads of family) |  | 1,934 families, 80% | 1,934 families | 1,934 families
|  | Port au Prince and surroundings areas |  |  | Provision of hygiene kits and bedding for 1200 people |  | 5,000 hygiene kits distributed + 84 baby kits to 84 pregnant women, 1,200 sheets distributed | 5,000 hygiene kits distributed + 84 baby kits to 84 pregnant women, 1,200 sheets distributed | 5,000 hygiene kits distributed + 84 baby kits to 84 pregnant women, 1,200 sheets distributed | 1200 |  |  | 1,200 families | 1,200 families
|  | Port au Prince and surroundings areas |  |  | Provision of 1200 survival kits (batteries, candles, flashes and matches) and 1200 kitchen kits |  | 1,200 families received survival kits and kitchen kits | 1,200 families received survival kits and kitchen kits | 1,200 families received survival kits and kitchen kits |  |  | 1,200 families, 100% | 1,200 families | 1,200 families
|  | Port au Prince and surroundings areas |  |  | Provision of 1200 water container (2 per family) for 600 families |  | 600 water containers of 19 Liters distributed |  |  |  |  | 600 families, 100% | 600 families | 600 families
|  | Port au Prince and surroundings areas |  |  | Provision of cooking utensils for 3 camps (2 with SHO funds) |  |  | cooking utensils for 2 camps were provided | cooking utensils for 2 camps were provided | 1000 families in 3 camps (2 with SHO funds) |  |  | 700 families | 700 families
|  | Port au Prince (St Martin area), Petit Goave, Jacmel |  |  | not planned originally |  | 8,100 emergency cots distirbuted | 8,100 emergency cots distirbuted | 8,100 emergency cots distirbuted |  |  | 8,100 individuals | 8,100 individuals | 8,100 individuals
|  | Port au Prince Bay (Carrefour) |  |  | Provision of 168 tool kits, 2000 kitchen kits, 2000 mattress pads, 2000 jerry cans, 2000 tarps, 2000 blankets |  | 6000 kitchen sets, 6000 hygiene kits, 500 tool kits, 12000 jerry cans, 12000 tarps, 12000 blankets and 4200 mosquito nets distributed (with SHO funding 6000 hygiene kits and 6 of the items of the 500 tool kits) | 6000 kitchen sets, 6000 hygiene kits, 500 tool kits, 12000 jerry cans, 12000 tarps, 12000 blankets and 4200 mosquito nets distributed (with SHO funding 6000 hygiene kits and 6 of the items of the 500 tool kits) | 6000 kitchen sets, 6000 hygiene kits, 500 tool kits, 12000 jerry cans, 12000 tarps, 12000 blankets and 4200 mosquito nets distributed (with SHO funding 6000 hygiene kits and 6 of the items of the 500 tool kits) | 2000 people |  | 6,000 individuals | 6,000 individuals | 6,000 individuals
5. Education | Education | Port au Prince and surroundings areas | Port au Prince and surroundings areas: Delmas 33, Christ-Roi, Liavois = (Croix des Bouquets), Belladere, Lascahobas, Thomassique & Fond Verrettes | Christian Aid with GARR | Support to 250 pupils for the period 2010-2011 |  | 1346 displaced children received US$ 20 for school related costs (50% with SHO funds) | 673 displaced children received US$ 20 for school related costs | 673 displaced children received US$ 20 for school related costs | 250 people |  | 1346 children (and 978 parents); 50% SHO funds | 673 children | 673 children
6. Shelter | Temporary | Port au Prince Bay (Carrefour) | Port au Prince, Petit Goave, Jacmel, Léogane: Saint Martin, Delmas 33, Christ-Roi, Liavois = (Croix des Bouquets), Belladere, Lascahobas, Thomassique & Fond Verrettes, Carrefour; Gressier | TSA; ADRA; local partners (ITECA, POHDH, RNDDH, POZ, SCH, FPH, KORAL, GRAMIR, GARR), CRWRC | 1485 tents supported by funds provided by ICCO & Kerk in Actie (from 1,800 tents planned) |  | 900 large size tents pruchased and distributed (with SHO funding 564 tents purchased and distributed) | 900 large size tents pruchased and distributed (with SHO funding 564 tents purchased and distributed) | 900 large size tents pruchased and distributed (with SHO funding 564 tents purchased and distributed) |  |  | 900 families (564 families with SHO funding) | 564 families | 564 families
[5 empty] | 210 semi-permanent shelters |  | 210 semi-permanent shelters constructed | 210 semi-permanent shelters constructed | 210 semi-permanent shelters constructed | 210 households |  | 210 families, 100% | 210 families | 210 families
|  | Port au Prince (St Martin area), Petit Goave, Jacmel |  |  | Shelter for 12,000 people living on and around a large soccer field, behind the main Salvation Army compound in the St Martin area of Port-au-Prince. 800 family tents have been distributed in the above area around its compound |  | 2,000 tents and 600 housing lumbers funded through SHO | 2,000 tents and 600 housing lumbers funded through SHO | 2,000 tents and 600 housing lumbers funded through SHO | 800 families |  | with SHO fundings, 2000 tents = 250% | 2,000 families | 2,000 families
[5 empty] | Provision of 500US$ to 200 staff members for personal recovery (rent, furniture, etc.) |  | 215 staff members received 500US$ for personal recovery (rent, furniture, etc.) | 215 staff members received 500US$ for personal recovery (rent, furniture, etc.) | 215 staff members received 500US$ for personal recovery (rent, furniture, etc.) | 200 people |  | 215 people | 215 people | 215 people
|  | Leogane: Masson, Macombe, Luitor and Croix des Peres |  |  | 225 transitional shelters are built with SHO funds (among the 1200 planned in the project) |  | 400 transitional shelters (80 with SHO funding) | 241 houses with SHO funds | 241 houses with SHO funds | 225 households |  | 80 households | 241 households | 241 households
7.Disaster management | Capacity building |  | Port au Prince: Delmas 33, Christ-Roi, Liavois = (Croix des Bouquets), Belladere, Lascahobas, Thomassique & Fond Verrettes | Christian Aid with GARR; DCA/World Vision with Sphere | Training on disaster risk reduction for partner staff |  | 1 session for 13 people from 7 CAID partners and 14 community members and 5 CA staff | 1 session for 13 people from 7 CAID partners and 14 community members and 5 CA staff | 1 session for 13 people from 7 CAID partners and 14 community members and 5 CA staff |  |  | 32 people trained | 32 people | 32 people
|  | Port au Prince and surroundings areas |  |  | Building of 3 Community Infrastructure |  | construction of 5 community infrastructure (3 with SHO funds): warehouse providing temporary shelter, school repairs, toilet and shower blocks in 4 camps, 3 drainage systems and contribution to construction of children's park | construction of 5 community infrastructure (3 with SHO funds): warehouse providing temporary shelter, school repairs, toilet and shower blocks in 4 camps, 3 drainage systems and contribution to construction of children's park | construction of 5 community infrastructure (3 with SHO funds): warehouse providing temporary shelter, school repairs, toilet and shower blocks in 4 camps, 3 drainage systems and contribution to construction of children's park | 1,200 families |  | 1,200 families | 1,200 families | 1,200 families
|  | Port au Prince and surroundings areas |  |  | 3 trainings for maintenance and management of areas |  | public space maintenance and environmental training conducted in 5 municipalities (3 funded by SHO) | public space maintenance and environmental training conducted in 5 municipalities (3 funded by SHO) | public space maintenance and environmental training conducted in 5 municipalities (3 funded by SHO) | 1,200 families |  | 1,200 families | 1,200 families | 1,200 families
|  | Port au Prince and surroundings areas |  |  | 3 trainings / awareness Human Rights |  | 567 people received training Human rights, violence women, women'rights, early pregnancy | 567 people received training Human rights, violence women, women'rights, early pregnancy | 567 people received training Human rights, violence women, women'rights, early pregnancy |  |  | 567 people | 567people | 567 people
|  | Port au Prince and surroundings areas |  |  | vocational training for young people |  |  | 30 young people received training and established micro-enterprises (50% SHO funds) | 30 young people received training and established micro-enterprises (50% SHO funds) | 50 young people |  |  | 15 young people | 15 young people
[5 empty] | Support of Sphere team: establishing local capacity; creation of Accountability and Learning Working Group |  | NA | capacity of humanitarian actors, government and local civil society has been strengthened with regard to knowledge of Sphere standards and indicators | capacity of humanitarian actors, government and local civil society has been strengthened with regard to knowledge of Sphere standards and indicators | not known at moment of planning |  | NA | 429 staff; and 44 trained as ToT | 429 staff; and 44 trained as ToT
8. Protection |  | Non applicable | not applicable | Christian Aid with GARR |  |  | local partner took part in meetings in Washington, New York, Santo Domingo and Port au Prince to voice out the rights of Haitian Civil Society Organisation, in the reconstruction of Haiti | local partner took part in meetings in Washington, New York, Santo Domingo and Port au Prince to voice out the rights of Haitian Civil Society Organisation, in the reconstruction of Haiti | local partner took part in meetings in Washington, New York, Santo Domingo and Port au Prince to voice out the rights of Haitian Civil Society Organisation, in the reconstruction of Haiti
|  | Non applicable |  |  |  |  | local partner participated in the conference for donors at the United Nations HQ on March 31st, 2010 | local partner participated in the conference for donors at the United Nations HQ on March 31st, 2010 | local partner participated in the conference for donors at the United Nations HQ on March 31st, 2010
9. Program management & support (at field level) |  | Port au Prince (St Martin area), Petit Goave, Jacmel | Port au Prince (St Martin area), Petit Goave, Jacmel | TSA, ICCO & Kerk in Actie local partners; ACT Alliance | Partner organisations have improved their capacity to respond to emergency |  | Project finalized with support from international partner to local organisation in Haiti | Project finalized with support from international partner to local organisation in Haiti | Project finalized with support from international partner to local organisation in Haiti | 1 |  | 1 team supported | 1 team supported | 1 team supported
[5 empty] | Rehabilitation and equipment of a training centre, 9 offices and |  | Training center reconstructed; old offices are rehabilitated and equipped; new offices rented (total 9 partners) | Training center reconstructed; old offices are rehabilitated and equipped; new offices rented (total 9 partners) | Training center reconstructed; old offices are rehabilitated and equipped; new offices rented (total 9 partners) | 9 offices and 1 training center |  | 9 offices and 1 training centre | 9 offices and 1 training centre | 9 offices and 1 training centre
[5 empty] | members international alliance coordinate interventions, trained on security and joined advocacy; implementation of joint evaluation |  | NA | ACT members have coordinated activities and programs; evaluation has been implemented | ACT members have coordinated activities and programs; evaluation has been implemented | 12 Forum member organisations |  | NA | NA | NA
200
125
100

## Compatibility Report
Compatibility Report for Report 5 table ICCO & Kerk in Actie 30-1-13.xls
Run on 30-01-2013 13:51
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 1 | Excel 97-2003